## Sheet1
Sprint | User story | Description | Tasks | Story points | Status
4 | BHPL 3.X: Create test cases & validate for recon &metadata services | Nabu Workspaces based Ingestion Pipeline with UO : Write test cases for Recon and Metadata services | Check for Sonarqube issue and resolve them | 5 | Completed
Develop test cases for Recon and Metadata REST services
Validate code coverage with the developed test cases
4 | BHPL-3.0 (PROD):- KOSH DB setup in deployed CLOUDSQL instance | Request for new CloudSQL instance creation for Kosh 3.0 and Set up Kosh 3.0. | CloudSQL instance request creation | 5 | Completed reqs and rolled over
Decommission of previous version of CloudSQL
Kosh Setup in newly deployed CloudSQL instance
4 | $U Mechanism: Integrate UDAP Snow ticket and email trigger feature with dollar u mechanism session checker rest client code - BHPL | Integrate the UDAP Snow ticket and email trigger feature with dollar u mechanism session checker rest client code for BHPL framework. | Integration of UDAP Snow ticket and Email trigger feature into Session checker client code | 3 | Completed integration but conn timedout issue
5 | BHPL 3.0 - Validating the existing Custom Code (Scala-Almaren) Pipelines in BHPL_pt2 | Validation of various types of ingestion jobs submitted through Nabu 3.0 using Azure databricks/Dataproc as compute. | Validate job submission to Azure Databricks | 3 | Completed
5 | BHPL-3.0 (PROD):- KOSH DB setup in deployed CLOUDSQL instance_pt2 | Request for new CloudSQL instance creation for Kosh 3.0 and Set up Kosh 3.0. | Follow up of CloudSQL instance creation | 5 | Completed
Kosh Setup after the instance creation
6 | $U Mechanism: T&Q Cloud Function - Existing code transition and configure the Dataprep 1.0 job trigger functionality. | Develop a Cloud Function code in the trigger and queueing mechanism Cloud Function. | Integration of BHPL onDemandIngestion endpoint in T&Q | 5 | Completed code and integration except validation of Dataprep
Integration of Dataprep onDemandIngestion endpoint in T&Q
Python code Development from existing code functionality of T&Q Cloud Function
6 | $U Mechanism: Integrate email trigger feature with dollar u mechanism session checker rest client code - BHPL | Integrate the UDAP Snow ticket and email trigger feature with dollar u mechanism session checker rest client code for BHPL framework. | Validation of feature after the firewall request | 3 | Completed